## Slide 1: Agenda
Project Name & Our Team members
Market Research
Project Structure
Methods of Implementation.
Project Outcomes.
Challenges.
Learned lessons.

## Slide 2: Implementing Oracle EBS Purchasing Module in 3MS pharmaceutical company
29-04-2025

## Slide 3: Team Members
Hend Yehia
Gehad Fahim
Mona Al Saadawi
Youstina Yousry

## Slide 4: Market Survey

## Slide 5: Market Survey

## Slide 6: Project Structure
1. Project Initiation
2. Requirements Gathering
3. Demo & Stakeholder Acceptance
4. Execution
5. Training & Documentation
6. Testing & Validation
7. Go-Live & Post-Go-Live Support
.

## Slide 7: 1-Project initiation
Kickoff Meeting: [1-1-2025]
  Project Objectives.
  Project Scope.
  Project Timeline
  Define Stakeholders
    General Manager (Mr. Ahmed Hassan )
    Financial Manager (Mr. Zaki Ahmed)
    Supply Chain Manager (Mr. Amir Fakry)
    Logistics Manager (Mr. Samy Ahmed)
  Methods of implementation (Hybrid)
    Water Fall
    Agile

## Slide 8: Project Objectives
Streamline Procurement Processes.
Enhance Supplier Management.
Optimize Inventory Control.
Improve Cost Efficiency.

## Slide 9: Project Scope
Limited to
The implementation of
The Oracle EBS Purchasing Module.

## Slide 10: Methods of Implementation
A hybrid implementation methodology,
  Requirements Gathering (Waterfall Approach).
  Configuration and Customization (Agile Approach)

## Slide 11: 2-Requirements Gathering
  Auto-generating Document Numbering by the system
    Requisitions
    RFQs
    Quotations
    Purchase Orders
    Receipt Number
  Never cancel a Requisition unless the requester cancels it.
  Notify the buyer if a Blanket PO Agreement exists.
  Price tolerance % between PR & PO doesn’t exceed 2% only.
  The ability to hold Supplier if Payables asked.
  Enforce Buyer Name.
Purchasing Requirements

## Slide 12: 2-Requirements Gathering
  Automatic Receipt Number Generation.
  Default Receipt Routing: Standard without inspection.
  Don’t allow unordered receipts.
  Allow receiving goods either 2 days earlier or 2 days later.
  Give a warning message only if the Receipt days exceed two days.
  The percentage variance allowed before a shipment is automatically closed for receiving is 5%. (Receipt Close Tolerance).
  We ask the Accounts Payable to provide us with these accounts to complete the configuration of receiving options
    Receiving Inventory Account
    Clearing Account
Receiving Requirements

## Slide 13: 2-Requirements Gathering
  We asked the Payable Accountant to provide us with the Accounts required for creating Procure to Pay journals:-
    Liability Account
    Prepayment Account
    Bills Payable Account
    Discount taken Account
    PO Rate Variance Gain Account
    PO Rate Variance Loss Account
    Expense AP Accrual Account
    Receiving Inventory Account
    Clearing Account
  Match the Approval Level between Invoice, Purchase Order, and Goods Receipt Note.
  Create a Journal at receipt for Accrue Expense items & Inventory Items.
Finance Requirements

## Slide 14: 3MS pharmaceutical Company Structure

## Slide 17: 3. Demo & Stakeholders Sign off Approval Document

## Slide 18: 4-Execution
  Creating the Operating Unit 3MS (Company Name)
  Legal location (Al Abour City).
  Using Vision Corporate as a Business Group.
  Using Vision Corporate as a Legal Entity.
  Using Vision operations (USA) Ledger.
  Creating a Master Item Organization (MAS).
  Creating an Inventory organization (M01).
  3 Sub-inventory organizations (RAW, Spare Parts, FGs).
.

## Slide 19: 4-Execution
  Defining items in the Master Item Organization and assigning them to M01 Inventory Organization.
.

## Slide 20: 4-Execution
  Define company departments as HR organizations.
    Top Management
    Finance
    Inventory
    Procurement
  Define users as employees in the HR Module.
    General Manager
    Financial Manager
    Supply Chain Manager
    Procurement Manager
    2 Buyers
    Inventory Manager
.

## Slide 21: 4-Execution
  Customizing responsibilities.
    Purchasing responsibility without the setup menu (New_Purchasing).
    Requesting Responsibility includes Purchase requisition (PR_Purchasing)
  Defining 8 System Profile options.
.

## Slide 22: 4-Execution
  Approval Groups
    1 Million
    2 Million
    3 Million
    Unlimited
    Assigning Approval groups to each position
  Position Hierarchy Approval Cycle
    Purchase Requisitions
    Standard Purchase orders.
    Blanket Purchase Orders.
  3-way matching
    Purchase order
    Receipt Note
    Invoice.
.

## Slide 23: 5-Training Business Users & Documentation
Training Business Users & Documentation
    Train procurement teams
      Procurement Managers.
      Buyers.
    Develop a user guide for all procurement processes.

## Slide 25: 6-Testing & Validation
Create Test Scenarios (Test Environment)
  Procure to Pay Complete Cycle
    Requisition No.:20251000010
    Approved Supplier List
    Bid RFQ No.:20252000005
    Quotations
      Approved Quotation:20254000007
      Unapproved Quotation:20254000008
    Converting quotation to Standard Purchase order
      Standard Purchase Order No.: 20253000038
  Requisition to Purchase Order :
  Requisition No.: 20251000007
  Standard PO No.:20253000027
  Return to Supplier after inspection.
    Standard PO No.:20253000026
    Receipt No.: 20255000001
    Item No: 3MS0017

## Slide 44: Sign-Off User Acceptance Test (UAT)
User Acceptance Test (UAT) Sign-Off:
After successful testing, the customer signs off on the UAT document to confirm functionality.

## Slide 45: 6-Go-Live & Post-Go-Live Support
Migrate configurations and customizations from the testing environment to the production environment.
Go-Live.
Provide post-go-live support for a predefined period (30 days) to resolve any immediate issues.

## Slide 46: Project Outcomes from Stakeholders Feedback
1. Operational Impact
    Order processing time decreased by 60%, improving customer service.
    Procurement cycle time reduced by 80%, streamlining vendor management.
    Inventory accuracy improved to 95%, preventing stock variations.
2. User Adoption & System Usability
    85% of employees reported improved efficiency in daily tasks.
    70% adoption rate within the first month, with ongoing training for remaining users.
    90% reduction in manual data entry errors, enhancing accuracy.

## Slide 47: Implementation Challenges Faced our team
Challenge 1: Data Migration Issues
  Data Quality: Inaccuracy and completeness of data being migrated.
Challenge 2: User Adoption
Resistance to Change: Some employees resist changes to their established workflows and processes.

## Slide 48: Learned Lessons
1. Clear Communication with Business Users
Explain the benefits of the ERP system, addressing concerns about job security, workflow changes, and efficiency improvements.
2. Comprehensive Training Programs
Provide hands-on training tailored to different user roles to ensure employees feel confident using the new system.
3. Structured Data Migration Plan
  Develop a detailed data migration plan that includes data cleansing and validation.
  Perform multiple rounds of data migration testing to identify and resolve issues before go-live.

## Slide 49: Thank you
Questions?